## Estimation
Expert review |  | 3 points
Tasks | Durability | E = (a + 4m + b) / 6
1.Assessment of the volume and complexity of work | 1 year | E = (7 + 4*3 + 10) / 6 = 4,8
1.1 Goal | 1 week
1.2 Risk Assessment | 3 weeks
1.3 Drawing up documentation | 5 month
1.4 Working out of metrics for the project | 5 month
2.Determination of necessary resources and sources of their receipt | 1 year
2.1 Drawing up a financial plan | 2 month
2.2 Search for investors | 7 month
2.3 Identifying sources of supply of resources | 3 month
3.The architecture and design of the rocket | 1 year
3.1 Development of technical characteristics of the rocket | 4 month
3.2 Development of rocket design | 2 month
3.3 Determining the components of a rocket | 3 month
3.4 Missile modeling and prototyping | 3 month
4.Development of a rocket | 1 year
5.Software testing and verification of calculations | 3 years
6.Preparing for launch | 11 hours
6.1 Delivery of the rocket to the takeoff site | 3 hours
6.2 Mounting the rocket | 1 hour
6.3 Delivery of Tesla to the rocket | 6 hours
6.4 Loading Tesla into a rocket | 1 hour
Total amount of time | 7 years 11 hours

## Activity planning
№ | Activities
1 | Assessment of the volume and complexity of work
2 | Determination of necessary resources and sources of their receipt
3 | Definitions of the schedule, terms and key points
4 | Risk assessment and preparation of preventive countermeasures
5 | Distribution of duties and responsibilities
6 | Coordination of testing activities with the activities of project team members involved in other tasks
7 | Test closure activities

## Metrics
New Functional |  |  |  |  | Rate | Decline Rate = (Decline Issues/Closed Issues)*100 % Decline Rate = (7/15)*100% Reopen Rate =(Reopen Bugs+Closed Bugs) /Reopen Bugs *100% Reopen Rate =((8+15)/8)*100% Blocked Rate = (Total/Blocked)*100% Blocked Rate= (36/6)*100%
Status | Total | Severity
|  | Major | Critical | Blocked
Closed | 15 | 10 | 5 | 0
Reoped | 8 | 5 | 3 | 0 | 287,5
Blocked | 6 | 3 | 3 | 0 | 890,9
Decline | 7 | 5 | 2 | 0 | 600
Regression |  |  |  |  | Rate | Decline Rate = (Decline Issues/Closed Issues)*100 % Decline Rate = (1/3)*100% Reopen Rate =(Reopen Bugs+Closed Bugs) /Reopen Bugs *100% Reopen Rate =((2+3)/2)*100% Blocked Rate = (Total/Blocked)*100% Blocked Rate= (10/4)*100%
status | total | Severity
|  | Major | Critical | Blocked
Closed Issues | 3 | 2 | 1 | 0
Reopen Issues | 2 | 1 | 1 | 0 | 250
Decline Issues | 1 | 1 | 0 | 0 | 33,3
Blocked | 4 | 3 | 1 | 0 | 250